Annex C: Logical Framework – Approach 2 component

The outcome and related outputs are generic which will be refined for each selected country proposal

| Project title: On-demand country advisory services to improve synergies between social protection and Public Finance Management | Project duration: 38 months |
| --- | --- |
| Impact (Development Objective) | Extension of social protection coverage (population, benefit levels and contingencies) in partner countries preferably but not limited to those benefiting from EU funded budget support operations. |
| Results chain | Indicators | Baseline | Target | Means of verification | Assumptions |
| Outcome 1: A minimum of 10 countries receive on-demand high quality, gender-responsive, disability-inclusive technical advisory services that are relevant and produce technically, financially and politically feasible recommendations on how to improve the national social protection system, programmes or delivery mechanisms | Number of countries that have improved their social protection data collection and statistics, in particular on social protection financing | 0 | 8 | Project progress and evaluation reports National Statistical reports | Countries and EU delegations submit relevant proposals |
|  | Number of countries that have increased the number of national social protection programmes, for which improved data is available, including regarding disability- and gender- disaggregated data and qualitative information on the programmes’ gender and disability sensitivity are publicly available (by country, quantitative, qualitative information) | 0 | 8 | Project progress and evaluation reports Programe data |  |
|  | 1.3 Number of research studies supported by the programme | 0 | 1 | Research publication | Countries or EU delegations plan to carry out research |
| Output 1: Selection of 10 countries through a minimum of two call for proposals, based on criteria of relevance and sound operations | Number of requests received Number of requests selected | 0 0 | 15 10 | Programme records, OC meeting minutes | Country and EU delegations are interested and able to submit reports |
| Launch and dissemination of the calls for proposals Organisation of selection of requests through the operational steering committee |  |  |  |  |  |
| Output 2: Delivery of technical advisory services of high quality that are gender-responsive and disability-inclusive are delivered in the 10 selected countries | Number of countries receiving quality gender-responsive and disability-inclusive technical advisory services Number of countries where constituents express satisfaction with services received | 0 | 10 | Porgramme records | The programme is able to contract the relevant experts to implement the services |
| A multidisciplinary technical team is composed to deliver the services in line with the request | Number of teams | 0 | 10 | Project records | Projects will adopt a multi-sectoral, interdisciplinary approach |
| A process for the participatory implementation of the advisory services is established, to the extent possible drawing on existing consultation or dialogue structures | Number of countries with a process for participatory implementation Number of stakeholders included in the participatory process (per country) | 0 0 | 10 Min. 5 | Project reports, evaluation reports | Governments and EU delegations take on board the participatory approach |
| The evidence base is created to address the request, including information and data on gender, disability, shock-responsiveness, costs, financing and digitalization | 1.1.1 Number of schemes and programmes for which data is collected 1.1.2 Number of countries with data and information on gender 1.1.3 Number of countries with data and information on disability 1.1.4 Number of countries with data and information on shock-responsiveness 1.1.5 Number of countries with data and information on costs/ financing 1.1.6 Number of countries with data and information on new technologies | 0 0 0 0 0 0 | 10 10 5 3 10 3 | Project outputs Programme data | The data and information is available and shared at country level |
| Different scenarios to improve the social protection system, programme or delivery mechanisms (in line with the request) are identified - scenarios are designed ensuring coherence and coordination within the social protection system across sectors and administrative levels and beyond social protection sector and with related policy areas such as employment policies. | Number of scenarios identified (per country) Number of scenarios developed paying attention to cross-sectoral coherence and coordination Number of scenarios developed paying attention to coherence and coordination across administrative levels Number of scenarios developed paying attention to coherence and coordination with related policy areas | 0 0 0 0 | 3 5 5 5 | Project outputs | Relevant stakeholders participate in the discussion on formulating scenarios |
| The scenarios identified are analysed regarding their cost, financing sources, political economy implications, institutional capacity, technical feasibility and taking into consideration implications regarding their effects on gender, disability, shock-responsiveness and potential of using new technologies in their implementation | Number of scenarios that are costed Number of scenarios analysing political economy implications institutional capacity technical feasibility gender responsiveness disability inclusiveness potential of new technologies | 0 0 | 10 5 | Project outputs | The needed information is available and shared at country levels |
| Findings are disseminated so that national stakeholders, including social partners are well-informed about social protection needs and possible actions to address them | Number of dissemination events (per country) Number of stakeholders stating to have acquired better understanding of social protection and public finances as a result of the project (per country) | 0 0 | 1 More than half | Event materials (agenda, list of participants, reports), evaluation | Countries and EU delegations endorse the results and their disseminsation |
| Technical advisory services delivered are summarized in an outcome document (country report, strategy, roadmap, draft policy, etc.) | Outcome document available | No | Yes | Project progress report, Evaluation report | The work can be completed in time |
| Framework and tools for monitoring progress in implementing the project outcomes (country report, strategy, roadmap, draft policy, etc.) and progress in extending social protection are established | Progress monitoring framework or tools available | No | Yes | Project progress report, Evaluation report | Monitoring progress is a high priority of the project manager |
| Technical advisory services are backstopped by responsible Regional and HQ specialist | Number of backstopping missions (per country) | 0 | 1 | Project progress report, Evaluation report | There is need for technical back |