| Log Frame: |
| --- |
| Beneficiaries: Vulnerable and poor segment of the Ethiopian population |
| Project title: Improving synergies between Social Protection and Public Finance Management in Ethiopia |  |  |  |
| Results Chain | Indicators | Baseline | Target | Means of verification | Assumptions |
| Impact (Development Objective) Increased social protection coverage | Percentage of the population covered by UPSNP, RPSNP or CBHI | 31.4% * (latest data available for 2018/19) | 35.5% | World Bank report on PSNP and Ethiopian Health Insurance Agency report on CBHI | The country is economically and politically stable after election in August. More recent and updated information is available. |
| Outcome: Improving the social protection system for Ethiopia through a sustainable financing strategy ** | Percentage of social protection expenditure (RPNSP and UPSNP and CBHI) from total public spending | 4% (latest data available is for 2017/18) | 6% | MoF’s annual budget and expenditure reports MoLSA’s progress reports on social protection GTP 3 Reports (Social Protection section) | Economic and social policies are geared towards inclusive growth and poverty reduction through the expansion of social protection coverage. |
| Output 1: Financing strategy for Social Protection in Ethiopia with short-term and medium-term options | A short-term and medium-term financing strategy is designed, presented, and advocated for take up by the government. | No social protection financing strategy | A financing strategy is in place for the government to implement. | - Financing strategy is available | - Key stakeholders are able and willing to support the process. |
| Activities |  |  |  |  |  |
| 1.1 Building an evidence base for financing non-contributory social protection programmes (such as vulnerability analysis on COVID-19, an investment case for social protection and fiscal space analysis) |  |  |  |  |  |
| 1.2. Technical/Expertise contribution to actuarial valuation (contributory) |  |  |  |  |  |
| 1.3 Financing strategy for social protection for short-term and medium term options |  |  |  |  |  |
| 1.4. Awareness raising, workshops, and policy advocacy related to financing social protection |  |  |  |  |  |
| Output 2: Extending social security to informal economy workers and supporting wage legislation related to social protection. | - National policy, programme or plan of action designed for extending social security to informal economy workers. - Minimum wage legislation issued | 0 0 | 1 1 | - MoLSA’s policy/programme document prepared for SP extension to informal economy workers -Minimum wage proclamation | -Commitment of MoLSA and POESSA to the inclusion of the informal sector in the national social security system -Commitment of the government and social partners to engage in dialogue on minimum wage. -Establishment and functionality of the Wage Board. |
| Activities |  |  |  |  |  |
| 2.1 Technical assessment to extend social security to informal sector workers including COVID-19 social protection responses |  |  |  |  |  |
| 2. 2. Awareness raising through media and/or stakeholders' workshops (Federal/Regional) for consensus building on the extension of social security to informal economy workers including COVID-19 social protection responsive programmes |  |  |  |  |  |
| 2.3 Tripartite consultation among government, workers’ and employers’ representatives on minimum wage and related social protection schemes |  |  |  |  |  |
| Output 3: Building the capacity of MoLSA to effectively monitor the social protection system. | - MoLSA is more effectively coordinating social protection programming through a functional social protection council/platform. | 0 social protection platforms | 1 functional platform | - Regular minutes of council/platform meetings - Public access to social protection information. - Monitoring reports from MoLSA/BoLSA (AA) | - The government approves the establishment of the social protection council. - Timely documentation (MoLSA provides timely reporting) - Efficient resourcing (MoLSA receives sufficient budget) |
|  | - MoLSA has a functional knowledge management platform and monitoring system for social protection programming. | 0 knowledge management platform | 1 knowledge management platform and established monitoring processes led by MoLSA |  |  |
| Activities |  |  |  |  |  |
| 3.1 Support MoLSA and Addis Ababa BoLSA develop monitoring tools and processes to better implement and track social protection programming. |  |  |  |  |  |
| 3.2 Increasing the capacity of MoLSA to facilitate the establishment of effective coordination mechanisms for social protection policy and strategy |  |  |  |  |  |
| 3.3 Developing a knowledge management platform for inclusive social protection (a possible example among others could be the Social Security Inquiry (SSI) which is a monitoring tool for social protection) |  |  |  |  |  |

* The total number of individuals under the UPSNP, RPSNP or CBHI divided by total population (population numbers are taken from Ethiopian Centre for statistical Agency’s projections).

** Outcome level indicators were limited to these due to lack of complete data for other programmes.