Social Protection Floor initiative

Thailand Social Protection Joint Team Meeting, Jan. 14

- Venue: ILO meeting room, UN services building, 11th floor

- Time: 13:30-16:30

- Present:

- UNICEF: 	Mr. Andrew Claypole

- UNICEF: Mrs Chayanit Wangdee

- UNFPA: Ms Chuangwiwat Viennarat

- WHO: Mr. Somchai Peerapakorn

- Mr Babar Sobhan

- ILO: Ms. Celine Felix

- Agenda:

- Update on the UNPAF process

- Review the first draft of the matrix

- Consultations with national counterparts

- Discussion, decisions & assignments:

- Update on the UNPAF process

After a session with the Joint team’s Chairs on Results Based matrices in December, Celine and Babar drafted this very first document based on previous consultations with the government and CSOs, and the DCS outcomes.

Babar reminded the group it was agreed that the outcomes should be as much as possible those stated in the national plan, in the case of social protection, the draft 11th Plan by NESDB. He added it would be possible to have an additional outcome which is cross-cutting.

Review the first draft of the matrix

A discussion was held on the four outcomes drafted and some wording changes were proposed. In order to further elaborate the matrix and consolidate outputs and outcomes, each organization presented his/her organization’s planned activities discussed with national counterparts in relation with social protection:

UNICEF: (with NESDB)

- Advocacy on the introduction of child allowance

- Technical support through research evidence including feasibility study, knowledge sharing on international good practices, stakeholders hearings/ public debate, costing, operation research

UNFPA

Target of work: older people, migrants, the youth, caregivers

- Ageing: expansion of coverage and more adequate protection with the Bureau  of Older Person Empowerment (MDHS) and other concerned stakeholders

  - Further evidence-based policy Advocacy on (non-contribution) Social Pension

  - Further Work on (contributory) pensions for the informal economy population i.e. integration of social security for informal sector and the National Saving Fund (SSO+ CSOs)

  - Gender/Feminization and ageing

  - Income and job opportunities for older people (MoL) [Potential collaboration with ILO and UNESCO to be explored]

  - Rights of older persons (HAI) [this area is recommended to be included in the Right Protection]

  - Social care / Long term care with the Health Security Office (  dependency) [Policy advocacy for welfare and social support for caregivers]

  - Information Hub i.e. Knowledge Sharing on Ageing

- Migration: Evidence-based policy advocacy for a comprehensive and coherent policy in response to the demographic change and the increasing demand in migrant labour.

[Potential collaboration with ILO and IOM to be explored]

WHO

Mr Somchai explained the group the alignment of the organization to adapt its work with MICs. Thailand was mentioned as a pilot country for this purpose. WHO is in a process of developing its new country cooperation strategies for Thailand covering the period 2011-2015, working with different national health authorities which are all independent and government-owned (notably NHCO, HRSI, NHSO, ThaiHealth, etc) on 5 programme areas, including community health system which can be linked to social protection. As usual WHO sees its potential to contribute in the area of social protection floor through its expertise in health financing.

ILO (with MoL , SSO, MoF)

- Work on assessing current social protection systems,

- Costing

- Extension to the informal economy

- Linkages between social protection and return to employment

Remarks and follow up:

-     It was highlighted that fiscal space analysis should be added as common work

-  	UNESCO is to provide inputs

-    Celine will review the matrix based on the inputs to be presented to the UNCT retreat next week (20-21 January)

-     Further developments will include agency-specific responsibilities attached to the key actions, indicators and their baselines.

- Consultations with national counterparts

Bilateral discussions with national counterparts lead to the conclusion that MDHS would be the leading agency on the national part

The group expressed that the outputs and outcomes proposed were from a series of consultations and ongoing work with the national counterparts, which already ensures the necessary ownership.

In order to discuss it further with Thai governments, Academia (TDRI, Chula university), and CSOs, get guidance of the overall UNPAF process by the government, and materialize the Joint Team on Social Protection with all stakeholders, the team will have meetings with the main actors identified after the UNCT retreat.

Follow-up:

- All members of the Team complete the list of stakeholders provided by Celine

- Adjourned at 16.30 hours