## Workplan
EU Joint Action Work Plan - UGANDA
Duration of Implementation: October 1, 2019 - May 30, 2023 (44 months)
Overall objective: To increase the population's universal social protection coverage in partner countries preferably but not limited to those benefiting from EU funded budget support operations
Outcome/s and Result/s | Annual target/s |  |  | List of activities | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  | Responsible PUNO/s | Implementing partner/s involved
| 2020 | 2021 | 2022/23 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Outcome (SO 1): To improve partner countries’ design and financing of social protection systems in support of their efforts towards SDGs 1 and 10. |  |  |  | Support to the GoU in publishing programmatic documents and establishing mechanisms to scale and sustain SP for children | [13 empty] | UNICEF | MoGLSD / KCCA
Result (R 1.1): Increased dialogue and coherence among sectors for the sustainable and adequate financing of universal social protection | Participation in at least 3 coordination meetings with government, donors, and/or CSOs per year | Participation in at least 3 coordination meetings with government, donors, and/or CSOs per year | Participation in at least 3 coordination meetings with government, donors, and/or CSOs per year | A.1.1.1a Technical support for the implementation of the National Social Protection Policy; Participation in sector working groups and steering committee meetings; | [13 empty] | UNICEF | MoGLSD / KCCA | bar: 2020 Q4; 2021 Q4; 2023 Q2
| Facilitate at least 3 national dialogue meetings | Compile national dialogue report |  | A.1.1.1b Assessment Based National Dialogue (ABND) Social Protection Policy Options Toos (SPPOT) | [13 empty] | ILO | bar: 2020 Q4 to 2021 Q4
| Facilitate at least 2 CSO and TU advocacy activities | Facilitate at least 4 CSO and TU advocacy activities | Facilitate at least 5 CSO and TU advocacy activities | A.1.1.2 Facilitate civil society and trade union advocacy activities towards key social protection policy and budgetary processes for improved and expanded social protection | [13 empty] | HAI | Uganda Social Protection Platform, relevant trade unions | bar: 2020 Q3 to 2023 Q1
Result (R 1.2): Enhanced evidence and availability of tools that support national evidence-based decision-making and encourage supra-national coordination and benchmarking of good practices (including the portability of social entitlements as integral part of economic and labour policies, gender-sensitive and disability inclusive social protection), with participation of regional bodies as well as civil society organisations. | Research coordination, data collection, and coordination with government and other stakeholders; 1 policy brief on key issues of SP and PFM published; | 3 operational research studies implemented and leveraged for evidence-based decision-making by GoU; 1 policy brief on key issues of SP and PFM published; | 2 qualitative research studies on gender- and age-responsive social protection completed; 1 policy brief on key issues of SP and PFM published; | A.1.2.1a Qualitative research studies on gender- and age-responsive social protection; A.1.2.1b Quantitative administrative and policy advocacy data, as well as operational research in the context of KCCA's urban social protection programme for adolescent girls; A.1.2.1c Development of policy advocacy briefs on key issues of SP and PFM that support KCCA in advocating for increased investments in social protection for vulnerable groups with MoFPED and others; | [13 empty] | UNICEF | MoGLSD / KCCA / MoFPED / | bar: 2020 Q4; 2021 Q4; 2023 Q1
| Research on informal and rural economy economy |  |  | A.1.2.1d Study on informal and rural economy, including recommendations for increasing coverage and exploring innovative financing options (ILO) | [13 empty] | ILO | MGLSD | bar: 2020 Q3 to 2021 Q2
| Actuaurial review of NSSF |  |  | A.1.2.1e Governance and administrative review of National Social Security Fund | [13 empty] | ILO | NSSF | bar: 2020 Q4 to 2021 Q4
| Research on social accountability mechanisms for social protection |  |  | A.1.2.1f Study on the effectiveness of Uganda’s social accountability mechanisms in improving the design and implementation of social protection programmes | [13 empty] | HAI | Uganda Social Protection Platform | bar: 2021 Q1 to 2021 Q4
| 2 policy briefs on impact of social protection programmes |  |  | A.1.2.1g Civil society advocacy policy briefs on expanded and improved social protection, impacts of Uganda’s social protection programmes and voices of beneficiaries (based on social accountability initiatives) age, gender and disability lens (HAI) | [13 empty] | HAI | Uganda Social Protection Platform | bar: 2021 Q3 to 2021 Q4
Outcome (SO 2): To support the government in implementing and monitoring effective gender-sensitive and disability-inclusive social protection systems and programmes for all while ensuring financial sustainability and macroeconomic stability. |  |  |  | Support to the GoU and collaboration with key stakeholders towards the development and piloting of a shared civil society social accountability approach | [13 empty] | HAI | GoU, CSOs
Result (R2.1): Strengthened capacities of partners to achieve the best impact of diversified sources of funding for social protection, prioritizing children, workers in the informal sector, and older persons. | At least 2 strategically selected officials from MoFPED, KCCA, NSSF, and/or MoGLSD supported to attend PFM and SP training (ILO) | At least 2 strategically selected officials from MoFPED, KCCA, NSSF, and/or MoGLSD supported to attend PFM and SP training (ILO) | At least 2 strategically selected officials from MoFPED, KCCA, NSSF, and/or MoGLSD supported to attend PFM and SP training (ILO) | A.2.1.1 Support for strategically selected government officials to participate in PFM and SP training (ILO) | [13 empty] | ILO | MoFPED, KCCA, NSSF, and/or MoGLSD | bar: 2020 Q4 to 2021 Q1; 2021 Q4; 2022 Q4
| Support CSO participation in at least 1 international peer learning event on SP and PFM | - | Support CSO participation in at least 1 international peer learning event on SP and PFM | A.2.1.2 Facilitate international peer-learning and knowledge exchange on social protection and PFM | [13 empty] | HAI | Uganda Social Protection Platform; GCSPF target countries in Action | bar: 2021 Q4; 2023 Q1
| CSO and TU training manual on SP and PFM developed; At least 60 CSO and Trade Union members are trained on social protection and public financial management | At least 60 CSO and Trade Union members are trained on social protection and public financial management | At least 30 CSO and Trade Union members are trained on social protection and public financial management | A.2.1.3 Increase capacity of CSO and Trade Union members on social protection, public financial management | [13 empty] | HAI | Uganda Social Protection Platform, relevant trade unions | bar: 2020 Q3 to 2021 Q1; 2021 Q3; 2022 Q1
Result (R 2.2): Strengthened knowledge and technical capacities of partner countries at national and sub-national levels to plan, deliver, monitor and report on social protection programmes, with participation of training institutions and civil society | Support for 6 gov. officials to attend relevant SP conferences (UNICEF supporting 4, ILO supporting 2); |  |  | A.2.2.1 Build the capacity of national policymakers for planning and management of social protection programmes through knowledge-sharing and coordination activities, including supporting the participation of government officials in relevant SP conferences; | [13 empty] | UNICEF, ILO | MoGLSD / KCCA / WB | bar: 2020 Q3; 2021 Q4; 2022 Q4
| Develop a civil society approach to grassroots/ community-based social accountability for relevant social assistance programmes | Pilot the approach to grassroots/community-based social accountability for relevant social assistance programmes | - | A.2.2.2 Develop and pilot a shared civil society approach to grassroots/community-based social accountability for relevant social assistance programmes | [13 empty] | HAI | Uganda Social Protection Platform | bar: 2020 Q3 to 2021 Q3
| At least 30 CSOs are trained on grassroots/ community-based social accountability | - | - | A.2.2.3 Increase capacity of CSOs on grassroots/community-based social accountability | [13 empty] | HAI | Uganda Social Protection Platform | bar: 2020 Q4
| Integration of urban social protection into the KCCA strategy; | One programme document on urban social protection programme for adolescent girls; | One M&E Framewrok established and implemented; | A.2.2.4 Support to GoU (KCCA) in the development of programmatic documents for their urban social protection programme for adolescent girls; Support to GoU (KCCA) in establishing mechanisms to sustain and scale SP for children; | [13 empty] | UNICEF | MoGLSD/KCCA | bar: 2021 Q1; 2022 Q1; 2022 Q4
| At least one multi-stakeholder dialogue event to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP | At least one multi-stakeholder dialogue event to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP | At least one multi-stakeholder dialogue event to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP | A.2.2.5 Organise multi-stakeholder dialogue events to improve delivery and monitoring processes, and address key issues pertaining to PFM and SP | [13 empty] | ILO | GOU, DPs, CSOs, UNICEF, HAI | bar: 2020 Q4; 2021 Q4; 2022 Q4