## Workplan
SP&PFM Project (EC-INTPA)- Work plan for the year 2021
Timeframe | Actual timeframe |  | Revised timeframe
Color indicator
Outcome
Output | Annual target/s |  | List of activities | 2020 |  | 2021 |  |  |  | Total Cost (USD) | Implementing partners involved | Comments
| 2020 | 2021 |  | Q3 | Q4 | Q1 | Q2 |  | Q3 | Total Cost (USD)
Specific Objective 1 – Technical support for the design and implementation of wage subsidies and employment retention in response to the COVID-19 crisis |  |  |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 1.1: A beneficiary identification criteria for wage subsidy disbursement programme for the formal sector workers developed. | One benificiary criteria developed | NA | 1.1.1 Review existing beneficiary identification criteria of ongoing social assistance/cash transfer programme for the RMG sector and similar cash transfer programme in ILO projects in other countries with RMG sector as well as other projects of development partners in Bangladesh. | [7 empty] | Triaprttie working committee:TWC (MoLE, BEF, BGMEA, BKMEA, NCCWE, IBC,), EU, MoSW, MoF
|  |  | 1.1.2 Draft an inclusive and gender responsive beneficiary identification criteria, which includes collecting feedback from tripartite plus constituents (civil society, NGOs, DPOs, DP partners), revise the draft and submitting the draft for endorsement by the tripartite working committee | [7 empty] | ILO, TWC & civil society, NGOs, DPOs, DP partners
Output 1.2: Design of a database of workers in line with the beneficiary criteria set above consolidated | Recommendation on the database for wage disbursement and employment retention compiled |  | 1.2.1 Coordination with EU technical assistance team in analysing the database of workers provided by BG/BKMEA | [7 empty] | EUD
|  |  | 1.2.2 Collect feedback from the workers representatives, NGOs, trade union bodies, civil society members on how to make this live database comprehensive and updated | [7 empty] | workers representatives, NGOs, trade union bodies, civil society members
|  |  | 1.2.3 Submit the compiled recommendations with the responsible database authorities in the EU and BG/BKMEA. | [7 empty] | EUD, BGMEA, BKMEA
Output 1.3: A grievance handling mechanism in the context of social assistance/ wage subsidy disbursement designed. | One grievance handling mechanism avilable for cash support initiatives |  | 1.3.1 Review existing grievance handling guideline for RMG factories | [7 empty] | DIFE, ILO projects-SDIR, BW
|  |  | 1.3.2 Draft an inclusive grievance handling mechanism which can be exported to other sectors of the economy in the context of wage subsidy to selected RMG workers including PWDs over a limited period of time | [7 empty] | ILO
|  |  | 1.3.3 Collect feedback from tripartite plus constituents and incorporate those into the draft. | [7 empty] | TWC & civil society, NGOs, DPOs, DP partners
|  |  | 1.3.4 Submit the draft grievance handling mechanism for endorsement of the working committee | [7 empty] | ILO
|  |  | 1.3.5 Share the grievance handling mechanism with relevant authorities including DP partners working on social assistance cash transfer/ wage subsidy initiatives for the RMG workers and beyond | [7 empty] | TWC & EUD
Output 1.4: A wage subsidy disbursement & employment retention mechanism for the formal sector workers designed. | One Wage subsidy disbursement mechanism designed |  | 1.4.1 Draft ToR for a disbursement expert and recruit a disbursement expert | [7 empty] | ILO
|  |  | 1.4.2 Review of existing disbursement mechanisms by Local Government Authorizes, Department of Social Welfare, NGOs, DPOs related to the RMG workers | [7 empty] | External disbursement expert
|  |  | 1.4.3 Bilateral consultations with mobile banking services on feasible mechanisms | [7 empty] | Bkash, Nagad, Rocket
|  |  | 1.4.4 Develop a design and protocol of inclusive wage disbursement mechanism. Propose linkages with wage subsidy with workers retention | [7 empty] | TWC
|  |  | 1.4.5 Consult with tripartite plus constituents on the draft design | [7 empty] | TWC & civil society, NGOs, DPOs, DP partners
|  |  | 1.4.6 Submit the draft design to the working committee after incorporating feedback | [7 empty] | TWC
Output 1.5: Technical inputs to the pilot testing for the wage subsidy disbursement mechanism developed | Technical input to pilot provided |  | 1.5.1 Techncial inputs to implementation plan of the wage subsidy disbursement mechanism | [7 empty] | EU
|  |  | 1.5.2 Submit the draft implementation plan to the working committee | [7 empty] | TWC
Output 1.6: Technical assistance provided for the rapid impact assessment conducted under the interlinked BMZ project on wage subsidy disbursement | Technical input to impact assessment provided |  | 1.6.1 Technical inputs for the design and implementation of the rapid impact assessment. | [7 empty] | ILO
Total cost of Output 1 | [9 empty] | 119212
Specific objective 2: Design specific social protection mechanisms to counter the effects of exogenous economic shocks
Output 2.1 Preliminary feasibility assessment of an Unemployment Insurance in consultation with Government, Workers and Employers for Bangladesh’s formal sector conducted |  |  | 2.1.1 Analysis of the labour market and profile of the unemployed i.e. sectors of the economy, category of workers, type of contracts, unemployment structure including proportion of youth unemployment in the total unemployment, formal/informal, migrant workers, women participation in the labour market, wages trends and structure; key demographic | [7 empty] | External Labour Market expert | Under Q2, ToR for the national labour expert and National Legal expert will be developed, finalized and will be completed the hiring procedure of the consultant. It is anticipted that they will onboard by June'21.
|  | One feasibility assessment techncial note on feasibility of an UI | 2.1.2 Conduct Desk review of institutional feasibility including review process of employment services currently provided by the MoLE departments which has the potential for an UI scheme for the formal sector | [7 empty] | ILO
|  |  | 2.1.3 Perform preliminary actuarial projection on costing and financing of an UI in Bangladesh based on the available data | [7 empty] | ILO
|  |  | 2.1.4 Draft a ToR and recruit an expert for preparing a note based on the review of industry specific structure. | [7 empty] | External expert
|  |  | 2.1.5 Draft ToR for a legal expert to review and expand on the note prepared by ILO/UNQLO for a legal framework review, analysing existing provisions for severance payment, termination allowances, provisions for retrenchments, provision for layoff during pandemics, comparison of the existing provisions with the relevant ILO conventions and recommendations for introducing an UI in Bangladesh | [7 empty] | ILO & external national expert
|  |  | 2.1.6 A technical note on linkages between employment services, inclusion, re-skilling initiatives of the government and UI. | [7 empty] | ILO
|  |  | 2.1.7 A technical note with the analysis on political will and preparedness to introduce an UI. | [7 empty] | ILO
Output 2.2 Framework of an unemployment Insurance Scheme for the formal Sector in Bangladesh designed |  | One Framework for an UI designed | 2.2.1 Based on the activities under output 2.1, Draft ILO technical recommendation on framework of an Unemployment Insurance Scheme for the formal sector in Bangladesh. | [7 empty] | ILO
|  |  | 2.2.2. Conduct tripartite consultations on the draft framework | [7 empty] | TWC & civil society, NGOs, DPOs, DP partners
|  |  | 2.2.3 Submit the draft framework of a UI to the MoLE and Financial Institution Division of Ministry of Finance | [7 empty] | TWC
|  |  | 2.2.4 Submit an organogram, list of required human resource and capacity development requirements for introducing an UI in selected formal sector/s. | [7 empty] | Internal & External experts
Total cost of Output 2 | [9 empty] | 71074
Specific Objective 3: Strengthen the knowledge of stakeholders to introduce sustainable social protection programmes
Output 3.1: An advocacy strategy for introducing social insurance scheme targeting the key policy makers developed. |  | Three guidance note avialble for advocacy with respective tripartite partners | 3.1.1 Brief note on local stakeholders mapping for policy advocacy on social insurance with focus on Unemployment Insurance and Employment Injury Insurance Scheme. | [7 empty] | All relevant stakeholders including TWC & civil society, NGOs, DPOs, DP partners
|  |  | 3.1.2 Develop three brief guidance notes for advocacy with the tripartite constituents | [7 empty] | ILO
Total Cost of Output 3 | [9 empty] | 37505
Total Cost of three objectives | [9 empty] | 227791
Note on A36: Reza, Farjana: This output progress will depend on outout 2.1
Note on J2: Reza, Farjana: Q4 is added as decided uoto December'21