## Workplan
Work plan
Outcome
Output | Annual target/s |  | List of activities | [6 empty] | Implementing partners involved
| 2020 | 2021 |  | Q4 | Q1 | Q2 | Q3 | Q4 | Total Cost
Output 1 | Completion of 10 per cent of the output | Completion of 90 per cent of the output | Support the Government to improve the design of social protection COVID-19 intervention measures addressed to workers in tourism sector. More specifically, collaborate in fine-tuning the criteria and qualifying conditions to select individual business households and informal workers eligible to cash transfers as announced by the Government. | [5 empty] | 55200 | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Support the Government in the rapid development of methodologies, processes and tools for the quick identification, registration and certification of possible beneficiaries, as well as for the rapid and safe delivery of benefits. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Promote dialogue between Government, Employers’ and Workers’ representatives in the tourism to contribute to the development of methodologies, processes and tools for the quick identification, registration and certification of possible beneficiaries, as well as for the rapid and safe delivery of benefits. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Undertake costings of these options and additional approaches recommended by the ILO to adapt or scale-up the existing social protection system, with a view to extending coverage to workers in the tourism sector. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Provide capacity building, especially at decentralized level (including employers representatives and trade unions in the tourism sector), and on newly introduced crisis response measures for effective delivery of the COVID-19 social protection measures. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
Output 2 | Completion of 10 per cent of the output | Completion of 90 per cent of the output | Undertake survey on the economic situation and characteristics of self-employed and micro and small enterprises, including an analysis of their protection needs, priorities and their contributory capacity. | [5 empty] | 46000 | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Promotion of Social Dialogue, including representatives of workers in the informal sector, to discuss options for the extension of social protection coverage. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Review of the available social protection options to workers in non- standard forms of work and development of policy recommendations for the extension of coverage. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Undertake costings of these options and additional approaches recommended by the ILO to adapt or scale-up the existing social protection system. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon
|  |  | Prepare some preliminary orientations on options for expanding fiscal space and financing for a sustainable social protection system in Sri Lanka. | [6 empty] | Ministry of Labour, Sri Lanka Tourism Development Authority, and Employer Federation of Ceylon